## Project schedule
| Final project |  | Dr. Florian Hastreiter |  |  |  |  | Project start: | [7 empty] | 2026-08-20
| WBS Coding School | [6 empty] | Display week: | [7 empty] | 1
| Explainable Machine Learning for Anomaly Detection and Fault Diagnosis in Batch Distillation |  |  | Due Date: | 2026-09-17
|  |  |  | Days Left: | 13 |  |  | 34 | [6 empty] | 35 | [6 empty] | 36 | [6 empty] | 37 | [6 empty] | 38 | [6 empty] | 39 | [6 empty] | 40 | [6 empty] | 41
| TASK | DELIVERABLE | PROGRESS | DURATION | START | END | time axis 2026-08-17 to 2026-10-11
[8 empty] | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
| 1. Data & Problem Definition | M1 – Data Ready | 100% | 6 | 2026-08-20 | 2026-08-26 | 7
| Project setup & dataset download | Data available, project structure | 100% | 1 | 2026-08-20 | 2026-08-20
| Dataset documentation & structure | Understand files, experiments, variables | 100% | 1 | 2026-08-21 | 2026-08-21
| Sensors & actuators analysis | Variable overview | 100% | 1 | 2026-08-22 | 2026-08-22
| Anomaly labels & metadata | Understand target/fault structure | 100% | 1 | 2026-08-23 | 2026-08-23 | 1
| Data quality analysis | Missing values, duplicates, outliers | 100% | 1 | 2026-08-24 | 2026-08-24 | 1
| Define ML problem & evaluation strategy | Target + train/test strategy | 100% | 1 | 2026-08-25 | 2026-08-25 | 1
| Define ML problem & evaluation strategy | M1 – Data Ready | 100% | 1 | 2026-08-26 | 2026-08-26
| 2. EDA & Feature Engineering | M2 – First Model | 81.43% | 6 | 2026-08-27 | 2026-09-02 | 7
| Sensor EDA | Distributions & patterns | 80% | 1 | 2026-08-27 | 2026-08-27
| Normal vs. anomaly analysis | Comparative analysis | 100% | 1 | 2026-08-28 | 2026-08-28
| Time-series analysis | Temporal patterns | 100% | 1 | 2026-08-29 | 2026-08-29
| Correlation & feature analysis | Feature relationships | 80% | 1 | 2026-08-30 | 2026-08-30 | 1
| Preprocessing pipeline | Clean data pipeline | 50% | 1 | 2026-08-31 | 2026-08-31 | 1
| Feature engineering | ML features | 80% | 1 | 2026-09-01 | 2026-09-01 | 1
| Baseline model | M2 – First Model | 80% | 1 | 2026-09-02 | 2026-09-02 | 1
| 3. ML Development | M3 – Model Freeze | 0% | 6 | 2026-09-03 | 2026-09-09 | 7
| Baseline model comparison | Initial benchmark | 0% | 1 | 2026-09-03 | 2026-09-03
| Random Forest / tree models | Advanced baseline | 0% | 1 | 2026-09-04 | 2026-09-04
| Gradient Boosting / XGBoost | Candidate model | 0% | 1 | 2026-09-05 | 2026-09-05
| Cross-validation & imbalance | Reliable evaluation | 0% | 1 | 2026-09-06 | 2026-09-06 | 1
| Hyperparameter tuning | Optimized candidates | 0% | 1 | 2026-09-07 | 2026-09-07 | 1
| Error analysis | Understand failures | 0% | 1 | 2026-09-08 | 2026-09-08 | 1
| Final model selection | M3 – Model Freeze | 0% | 1 | 2026-09-09 | 2026-09-09
| 4. Explainability & Validation | M4 – Analysis Freeze | 0% | 4 | 2026-09-10 | 2026-09-14 | 5
| SHAP implementation | Explainability pipeline | 0% | 1 | 2026-09-10 | 2026-09-10
| Global feature importance | Main drivers identified | 0% | 1 | 2026-09-11 | 2026-09-11
| Local explanations | Individual predictions | 0% | 1 | 2026-09-12 | 2026-09-12
| Fault/engineering interpretation | Compare ML vs. known faults | 0% | 1 | 2026-09-13 | 2026-09-13 | 1
| Final validation & visualizations | M4 – Analysis Freeze | 0% | 1 | 2026-09-14 | 2026-09-14
| 5. Finalization | M5 – Project Freeze | 0% | 1 | 2026-09-15 | 2026-09-16
| Code + documentation + README | Project finalized | 0% | 1 | 2026-09-15 | 2026-09-15
| Presentation + rehearsal | M5 – Project Freeze | 0% | 1 | 2026-09-16 | 2026-09-16
| Final presentation | FINAL | 0% | 1 | 2026-09-17 | 2026-09-17
Insert new rows ABOVE this one

## Sheet1
Task | Start | End | Duration | Status | Milestone | 1. Data & Problem Definition — 20–26 Aug
1. Data & Problem Definition | 2026-08-20 | 2026-08-26 | 7 | Not Started | M1 – Data Ready
2. EDA & Feature Engineering | 2026-08-27 | 2026-09-02 | 7 | Not Started | M2 – First Model | ID | Task | Est.
3. ML Development | 2026-09-03 | 2026-09-09 | 7 | Not Started | M3 – Model Freeze | 1.1 | Download / organize dataset | 2 h
4. Explainability & Validation | 2026-09-10 | 2026-09-14 | 5 | Not Started | M4 – Analysis Freeze | 1.2 | Understand dataset structure & documentation | 3 h
5. Finalization | 2026-09-15 | 2026-09-16 | 2 | Not Started | M5 – Project Freeze | 1.3 | Inspect experiments, sensors & actuators | 4 h
6. Final Presentation | 2026-09-17 | 2026-09-17 | 1 | Not Started | FINAL | 1.4 | Inspect anomaly labels & metadata | 4 h
[6 empty] | 1.5 | Define ML target(s) | 2 h
[6 empty] | 1.6 | Analyze class distribution | 2 h
Date | Main Task | Deliverable / Goal |  |  |  | 1.7 | Define train/test strategy | 2 h
2026-08-20 | Project setup & dataset download | Data available, project structure |  |  |  | 1.8 | Initial data-quality assessment | 4 h
2026-08-21 | Dataset documentation & structure | Understand files, experiments, variables |  |  |  | 1.9 | Document assumptions & project scope | 2 h
2026-08-22 | Sensors & actuators analysis | Variable overview |  |  |  | M1 | Data Ready
2026-08-23 | Anomaly labels & metadata | Understand target/fault structure
2026-08-24 | Data quality analysis | Missing values, duplicates, outliers |  |  |  | ~25 h
2026-08-25 | Define ML problem & evaluation strategy | Target + train/test strategy
2026-08-26 | Data preparation | M1 – Data Ready
2026-08-27 | Sensor EDA | Distributions & patterns
2026-08-28 | Normal vs. anomaly analysis | Comparative analysis |  |  |  | 2. EDA & Feature Engineering — 27 Aug–2 Sep
2026-08-29 | Time-series analysis | Temporal patterns
2026-08-30 | Correlation & feature analysis | Feature relationships |  |  |  | ID | Task | Est.
2026-08-31 | Preprocessing pipeline | Clean data pipeline |  |  |  | 2.1 | Explore sensor distributions | 3 h
2026-09-01 | Feature engineering | ML features |  |  |  | 2.2 | Explore actuator distributions | 2 h
2026-09-02 | Baseline model | M2 – First Model |  |  |  | 2.3 | Visualize normal vs. anomalous experiments | 4 h
2026-09-03 | Baseline model comparison | Initial benchmark |  |  |  | 2.4 | Analyze missing values / outliers | 3 h
2026-09-04 | Random Forest / tree models | Advanced baseline |  |  |  | 2.5 | Analyze temporal behavior | 3 h
2026-09-05 | Gradient Boosting / XGBoost | Candidate model |  |  |  | 2.6 | Investigate sensor correlations | 3 h
2026-09-06 | Cross-validation & imbalance | Reliable evaluation |  |  |  | 2.7 | Define preprocessing pipeline | 3 h
2026-09-07 | Hyperparameter tuning | Optimized candidates |  |  |  | 2.8 | Design feature-engineering strategy | 3 h
2026-09-08 | Error analysis | Understand failures |  |  |  | 2.9 | Implement feature extraction | 5 h
2026-09-09 | Final model selection | M3 – Model Freeze |  |  |  | 2.1 | Build final ML dataset | 3 h
2026-09-10 | SHAP implementation | Explainability pipeline |  |  |  | 2.11 | Train first baseline model | 3 h
2026-09-11 | Global feature importance | Main drivers identified |  |  |  | M2 | First Model
2026-09-12 | Local explanations | Individual predictions
2026-09-13 | Fault/engineering interpretation | Compare ML vs. known faults |  |  |  | ~35 h
2026-09-14 | Final validation & visualizations | M4 – Analysis Freeze
2026-09-15 | Code + documentation + README | Project finalized
2026-09-16 | Presentation + rehearsal | M5 – Project Freeze
2026-09-17 | Final presentation | FINAL |  |  |  | 3. ML Development — 3–9 Sep
[6 empty] | ID | Task | Est.
[6 empty] | 3.1 | Establish baseline metrics | 2 h
[6 empty] | 3.2 | Train baseline models | 4 h
[6 empty] | 3.3 | Train tree-based models | 4 h
[6 empty] | 3.4 | Cross-validation | 4 h
[6 empty] | 3.5 | Compare model performance | 3 h
[6 empty] | 3.6 | Handle class imbalance if required | 3 h
[6 empty] | 3.7 | Hyperparameter tuning | 5 h
[6 empty] | 3.8 | Error analysis | 4 h
[6 empty] | 3.9 | Investigate fault-category classification | 5 h
[6 empty] | 3.1 | Final model selection | 2 h
[6 empty] | M3 | Model Freeze
~36 h
4. Explainability & Validation — 10–14 Sep
[6 empty] | ID | Task | Est.
[6 empty] | 4.1 | Set up SHAP / explainability | 3 h
[6 empty] | 4.2 | Global feature importance | 3 h
[6 empty] | 4.3 | Local prediction explanations | 3 h
[6 empty] | 4.4 | Feature importance stability | 3 h
[6 empty] | 4.5 | Compare explanations with known faults | 4 h
[6 empty] | 4.6 | Process-engineering interpretation | 4 h
[6 empty] | 4.7 | Robustness / sensitivity checks | 4 h
[6 empty] | 4.8 | Final results & visualizations | 4 h
[6 empty] | 4.9 | Document limitations | 2 h
[6 empty] | M4 | Analysis Freeze
~30 h
5. Finalization — 15–16 Sep
[6 empty] | ID | Task | Est.
[6 empty] | 5.1 | Clean & organize code | 3 h
[6 empty] | 5.2 | Finalize notebooks / pipeline | 3 h
[6 empty] | 5.3 | Final README / documentation | 3 h
[6 empty] | 5.4 | Final figures & tables | 3 h
[6 empty] | 5.5 | Write conclusions | 2 h
[6 empty] | 5.6 | Prepare presentation | 5 h
[6 empty] | 5.7 | Presentation rehearsal | 2 h
[6 empty] | M5 | Project Freeze
~21 h
6. Presentation — 17 Sep
[6 empty] | ID | Task | Est.
[6 empty] | 6.1 | Final technical check | 1 h
[6 empty] | 6.2 | Final presentation rehearsal | 1 h
[6 empty] | 6.3 | Final Presentation | —